## Overview
Temu GTM — 30-Day Adoption Sprint ¦ Execution Tracker
Field | Detail
Sprint window | ~July 1 – July 30, 2026 (30 days)
North star — adoption | Activations (installs reaching first sync/list)
North star — revenue | Affiliate onboards (Temu US + UK)
Headline offer | 0% Temu selling commission, forever (via affiliate) + free app trial
Funnel spine | Acquire → Activate → Expand → Advocate
Channels | SalesIQ chatbot · CRM email cadences · Campaigns · In-app/Shopify banners
Apps in market | Temu Importer (store, manage-intent) · Temu Connector (custom, create-intent)
Routing | Q1 already on Temu? → affiliate if no. Q2 create on Temu? → Connector if yes, else Importer
Compliance guardrail | Importer public listing must NOT advertise upload/create-listing
Tabs | Funnel & Targets · Segments · 30-Day Calendar · Cadence Matrix · KPI Dashboard · Parking Lot

## Funnel & Targets
Funnel Assumptions & Computed Targets
ASSUMPTIONS (edit the blue cells)
Assumption | Value | Notes
UK affiliate signups — ACTUAL (last run) | 50 | Your real result: ~50 over 6–7 months
…over how many months | 6.5 | Duration of that run
US vs UK reach multiplier | 2 | US pool 10k = 2× UK 5k (assumes similar conversion)
0% commission hook uplift | 1.5 | Expected lift from the new hook (1.0 = no lift)
Warm Temu sellers in DB (FILL) | 0 | ENTER your warm manage-intent list size
Warm → install rate | 5% | Installs from the warm list
New onboard → install rate | 30% | Affiliate onboards that install
Install → activation rate | 70% | Installs reaching first sync/list
Trial → paid rate | 30% | Activated trials converting to paid
Existing custom-app users | 100 | Baseline provided
Existing → upgrade/cross-sell rate | 7% | Tier upgrade or Connector cross-sell
COMPUTED TARGETS (formula-driven)
Target metric | Value | Formula basis
UK affiliate onboards (sprint) | 11.5385 | UK run-rate × hook uplift
US affiliate onboards (sprint) | 23.0769 | UK run-rate × reach × uplift
Total affiliate onboards | 34.6154 | UK + US
App installs | 10.3846 | Onboards×install + warm×rate
Activations (north star) | 7.2692 | Installs × activation rate
Trial → paid conversions | 2.1808 | Activations × trial→paid
Tier upgrades + cross-sell | 7 | Existing users × upgrade rate
Reviews target: 5–12 (seeded from activated, satisfied users — qualitative). Targets are conservative; treat Week 1 as live calibration and update the blue cells with real rates.

## Segments
Audience Segments
Segment | Size | Stage | Offer / message | Owner
US sellers not on Temu | 10,000 | Acquire | 0% commission forever + free trial → onboard Temu US | [assign]
UK sellers not on Temu | 5,000 | Acquire | 0% commission forever + free trial → onboard Temu UK | [assign]
Existing Connector users | ~100 | Expand | Tier upgrade, retention, review request, tag create-intent | [assign]
Importer installs | ~0 | Activate / Advocate | Activation nudges + review seeding | [assign]
On-Temu, manage-intent | routed | Activate | Install Importer → first sync | [assign]
On-Temu, create-intent | routed | Activate | Use Connector → first listing (off public listing) | [assign]

## 30-Day Calendar
30-Day Sprint Calendar
Week | Theme | Key activities | Channel(s) | Owner | Status
Week 1 | Launch & acquire | Go live 0% hook campaign; chatbot qualify-and-route; start US/UK affiliate cadences; activation cadence to existing Temu sellers; baseline scorecard | Campaign, Chatbot, Email | [assign] | Not started
Week 2 | Scale & activate | Scale acquisition to full pools; activation nudges to new installs; switch on in-app Expand banners; first weekly review + prune variants | Email, In-app | [assign] | Not started
Week 3 | Optimize & advocate | Kill weak variants; double down on winners; launch review push to activated users; begin trial→paid nudges | Email, In-app | [assign] | Not started
Week 4 | Convert & expand | Final trial→paid push; tier upgrade + Connector cross-sell; tag create-intent; sprint wrap + metrics readout + retro | Email, In-app | [assign] | Not started

## Cadence Matrix
Cadence & Channel Matrix (context for Phase 2 copy)
Cadence | Stage | Trigger | Touches | Channel | Exit criteria | Status
Affiliate onboarding (US) | Acquire | Not on Temu, US region | 7 over ~28d | Email + Chatbot | Onboards / opts out / exhausted→nurture | To draft
Affiliate onboarding (UK) | Acquire | Not on Temu, UK region | 7 over ~28d | Email + Chatbot | Onboards / opts out / exhausted→nurture | To draft
Activate — install & first action | Activate | On Temu, routed by intent | 6 over ~13d | Email + In-app | Activation / opts out / trial lapse→win-back | To draft
Expand — upgrade & cross-sell | Expand | Activated or existing user | 3 ongoing | In-app + Email | Upgrade/cross-sell / opts out | To draft
Advocate — reviews | Advocate | Value milestone reached | 2 touches | In-app + Email | Review left / declined | To draft
Win-back | Re-engage | Trial lapsed, no activation | 3 over ~21d | Email | Reactivates / opts out / exhausted | To draft

## KPI Dashboard
KPI Dashboard — Target vs Actual
KPI | Target | Actual | Variance | % to goal
UK affiliate onboards | 11.5385 | 0 | -11.5385 | 0%
US affiliate onboards | 23.0769 | 0 | -23.0769 | 0%
App installs | 10.3846 | 0 | -10.3846 | 0%
Activations (north star) | 7.2692 | 0 | -7.2692 | 0%
Trial → paid | 2.1808 | 0 | -2.1808 | 0%
Tier upgrades + cross-sell | 7 | 0 | -7 | 0%
App-store reviews | 8 | 0 | -8 | 0%
Enter weekly actuals in the blue 'Actual' column; variance and % to goal update automatically.

## Parking Lot
Parking Lot — Future Convergence (no committed timeline)
Item | Detail
Convergence plan | Backend-enable upload in Temu Importer → one app does all → later rename listing to 'Shopify Temu Connector'.
Status | No confirmed timeline. Plan does NOT depend on it.
Action now | Tag create-intent sellers (create-intent / upload-waitlist) so a warm audience exists at launch.
Create-intent waitlist count | [track here — excluded from sprint targets]
Trigger to activate | Compliance paperwork cleared + backend upload enabled.